## All Dependencies
Dependency ID | Title | Description | Status | Feature | Priority | Program Increment | Depends On | Needed By | Blocked Reason
1 | Dependency Title 1 | Dependency Description 1 | No Commit | Feature 1 | Medium | Backlog | Team 1 | 2020-12-16
2 | Dependency Title 2 | Dependency Description 2 | No Commit | Feature 12 | Medium | Backlog | Team 2 | 2020-12-31
3 | Dependency Title 3 | Dependency Description 3 | No Commit | Feature 3 | Medium | Backlog | Team 2 | 2021-01-15
4 | Dependency Title 4 | Dependency Description 4 | Proposed | Feature 17 | Low | Backlog | Team 1 | 2021-01-05
5 | Dependency Title 5 | Dependency Description 5 | Committed | Feature 5 | Medium | PI 2 | Team 2 | 2020-12-20
6 | Dependency Title 6 | Dependency Description 6 | Committed | Feature 21 | Low | PI 1 | Team 3 | 2020-12-28
7 | Dependency Title 7 | Dependency Description 7 | Done | Feature 23 | Medium | PI 1 | Team 1 | 2020-11-29
8 | Dependency Title 8 | Dependency Description 8 | Committed | Feature 8 | Low | PI 1 | Team 3 | 2021-01-08
9 | Dependency Title 9 | Dependency Description 9 | Committed | Feature 11 | Low | PI 2 | Team 2 | 2020-12-21
10 | Dependency Title 10 | Dependency Description 10 | Committed | Feature 10 | Medium | PI 2 | Team 3 | 2021-01-15